## Goals
Goal ID | Goal Name | Goal Type | Problem Addressed | Category Intent | Technical Outcome | Governance / Regulatory Outcome | Vendor Outcome | IP Outcome | Success Criteria | Status | Notes
CM‑01 | Define AI Computational Memory as a distinct category from advisory behavior | Conceptual / Regulatory | Users must start from zero each session; no safe, structured persistence model exists. | Separate computational memory from advisory guardrails so memory can evolve without being treated as behavior | Session‑to‑session persistence of model structures (plans, strategies, decision engines). | Recognition that computational memory is a distinct object of regulation and governance. | Vendors expose and control computational memory separately from advisory guardrails. | Documented, defensible framing and implementation patterns. | Category definition accepted as non‑advisory functional layer. | Complete | Anchored by v1.0 white paper and GitHub category definition.
CM‑02 | Build the governance architecture for supervised continuity | Governance / Architecture | No regulated structure exists for safe persistence; guardrails trigger silent failures. | Define supervisory surfaces, validation gates, and regulated boundaries | Governed retention, transformation, deletion, and supervisory control surfaces. | Clear separation between advisory output and non‑advisory continuity. | Vendors can implement governed persistence without violating advisory constraints. | Governance architecture, regulated boundaries specification, enterprise controls checklist. | Architecture is regulator‑aligned and vendor‑implementable. | Complete | Delivered through v1.7 GitHub corpus and white paper.
CM‑03 | Deliver the supervised continuity test suite | Technical / Assurance | Enterprises cannot validate continuity behavior before deployment. | Provide deterministic, auditable tests for safe persistence | Eligibility tests, guardrail activation tests, transformation integrity tests, failure‑mode detection. | Pre‑deployment assurance for regulated environments. | Vendors can certify continuity behavior without exposing model internals. | Full test suite specification and continuity failure‑mode taxonomy. | Test suite is deterministic, auditable, and versioned. | Complete | Fully documented in GitHub v1.7 and white paper.
CM‑04 | Produce the complete v1.0 white paper | Category Definition / Enterprise Communication | No authoritative, enterprise‑grade articulation of computational memory exists. | Establish the canonical definition, architecture, controls, test suite, and use cases | Full conceptual and governance specification for computational memory. | Clear regulatory alignment and non‑advisory classification. | Vendors receive a complete blueprint for implementing governed persistence. | Category‑defining white paper with defensible conceptual spine. | White paper is complete, coherent, and enterprise‑grade. | Complete | Includes all H1s, Examples, FAQ, and version footer.
CM‑05 | Build the modular GitHub corpus (v1.0 → v1.7) | Technical / Documentation | No structured, versioned corpus exists for computational memory. | Provide a modular, navigable, versioned technical repository | Full directory structure, routing, release notes, diagrams, modular corpus. | Transparent, auditable documentation for regulators and governance teams. | Vendors can reference a stable, versioned corpus for implementation. | Complete GitHub repository defining the category and technical specification. | v1.7 corpus is stable, modular, and aligned with the white paper. | Complete | Includes release notes v1.0–v1.7, routing spine, modular structure.

## Phases
Phase ID | Phase Name | Phase Objective | Linked Goal ID(s) | Scope | Key Activities | Key Artifacts | Exit Criteria | Status | Notes
PH‑01 | Category Definition | Demonstrate that computational memory can persist across sessions without being conflated with advisory behavior. | CM‑01 | Focus on memory structures (state, plans, decision engines), not conversational outputs. | Session‑to‑session persistence of model structures (plans, strategies, decision engines). | Recognition that computational memory is a distinct object of regulation and governance. | Vendors expose and control computational memory separately from advisory guardrails. | Complete | Anchored by category definition and white paper conceptual spine.
PH‑02 | Technical Modeling of Computational Memory | Establish the technical constructs, representations, and transformation rules that define computational memory as a governed persistence layer. | CM‑02, CM‑03 | Model retention, transformation, deletion, and supervisory surfaces. | Build technical models, define continuity objects, specify transformation integrity rules. | Technical models for retention, transformation, deletion, and supervisory surfaces. | Continuity objects and transformation rules validated against governance architecture. | Complete | Delivered through v1.7 GitHub corpus.
PH‑03 | Session‑to‑Session Persistence Prototype | Demonstrate a working prototype of governed continuity across sessions using the defined memory structures. | CM‑01, CM‑02, CM‑03 | Prototype continuity behavior without triggering advisory guardrails. | Implement persistence logic, run eligibility tests, validate failure‑mode detection. | Session‑to‑session persistence prototype and continuity eligibility tests. | Prototype demonstrates governed continuity without triggering advisory guardrails. | Complete | Prototype behavior validated through continuity test suite.
PH‑04 | Governance & Regulator Engagement | Align computational memory with regulatory expectations and demonstrate clear separation from advisory behavior. | CM‑02, CM‑04 | Define regulated boundaries and supervisory controls. | Produce governance architecture, regulator‑aligned controls, and compliance framing. | Governance architecture, regulated boundaries specification, regulator‑aligned controls. | Clear regulatory separation between advisory behavior and computational memory. | Complete | White paper governance section and regulated boundaries finalized.
PH‑05 | Vendor Integration Patterns | Provide vendors with a complete, implementable blueprint for integrating computational memory safely. | CM‑05 | Deliver modular, versioned technical patterns for vendor adoption. | Publish GitHub corpus, release integration patterns, document continuity test suite. | Modular GitHub corpus, integration patterns, continuity test suite documentation. | Vendors can implement governed persistence using stable, versioned patterns. | Complete | v1.7 corpus published with routing spine and release notes.

## Deliverables
Deliverable ID | Deliverable Name | Deliverable Type | Description | Github Link / Location | Linked Phase ID | Linked Goal ID | Intended Audience | Status | Release Date | Signals / Adoption | Notes
DL‑01 | AI Computational Memory Category Definition | Conceptual / Regulatory | Canonical definition of the category, including problem framing, conceptual spine, and separation from advisory behavior. | ai-computational-memory/category-definition.md | PH‑01 | CM‑01 | Regulators, enterprise governance teams, vendors | Complete | "July 2026" | Category definition referenced across all subsequent artifacts; forms the conceptual spine for governance and vendor patterns. | Anchors the entire computational memory category.
DL‑02 | Session‑to‑Session Memory Structure Spec | Technical Specification | Formal specification of continuity objects (state, plans, decision engines), retention rules, and transformation integrity requirements. | ai-computational-memory/memory-structures/spec.md | PH‑02 | CM‑02, CM‑03 | Technical architects, model engineers, governance reviewers | Complete | "July 2026" | Memory‑structure terminology (state, plans, decision engines) adopted consistently across GitHub corpus and white paper. | Establishes the technical vocabulary for continuity objects.
DL‑03 | Prototype: Persistent Decision Engine for Financial Goals | Prototype / Technical Artifact | Demonstration of governed session‑to‑session persistence using a financial‑goals decision engine without triggering advisory guardrails. | ai-computational-memory/prototypes/persistent-decision-engine/ | PH‑03 | CM‑01, CM‑02, CM‑03 | Prototype evaluators, enterprise risk teams, vendors | Complete | "July 2026" | Prototype behavior validated through continuity test suite; demonstrates governed persistence without advisory guardrail activation. | Confirms feasibility of supervised continuity.
DL‑04 | Governance Architecture for Supervised Continuity | Governance / Architecture | Full supervisory surfaces, validation gates, regulated boundaries, and governance controls for computational memory. | ai-computational-memory/governance/architecture.md | PH‑04 | CM‑02 | Regulators, enterprise governance teams, compliance functions | Complete | "July 2026" | Governance architecture reused across regulated boundaries, test suite, and white paper governance chapter. | Provides the supervisory surfaces and control spine.
DL‑05 | Regulated Boundaries Specification | Regulatory Alignment | Definition of advisory vs non‑advisory boundaries, continuity eligibility rules, and regulator‑aligned separation. | ai-computational-memory/governance/regulated-boundaries.md | PH‑04 | CM‑02 | Regulators, governance architects, enterprise risk leaders | Complete | "July 2026" | Regulated boundaries referenced in FAQ, examples, and governance sections; aligns category with regulatory expectations. | Clarifies advisory vs non‑advisory separation.
DL‑06 | Continuity Test Suite (v1.7) | Technical / Assurance | Deterministic, auditable tests for retention eligibility, guardrail activation, transformation integrity, and failure‑mode detection. | ai-computational-memory/test-suite/v1.7/ | PH‑03 | CM‑03 | QA/assurance teams, enterprise risk, vendors | Complete | "July 2026" | Test suite used to validate prototype and continuity behavior; adopted as assurance baseline. | Establishes deterministic, auditable continuity validation.
DL‑07 | Failure‑Mode Taxonomy for Computational Memory | Technical / Risk | Structured taxonomy of continuity failure modes, supervisory triggers, and remediation patterns. | ai-computational-memory/test-suite/failure-modes.md | PH‑02, PH‑03 | CM‑03 | Enterprise risk, model governance, technical assurance | Complete | "July 2026" | Failure‑mode taxonomy integrated into governance architecture and test suite documentation. | Provides structured risk framing for continuity behavior.
DL‑08 | Modular GitHub Corpus (v1.0 → v1.7) | Documentation / Technical Repository | Complete versioned corpus including routing spine, release notes, diagrams, and modular structure. | ai-computational-memory/ | PH‑05 | CM‑05 | Vendors, enterprise architects, technical implementers | Complete | "July 2026" | GitHub corpus becomes the central reference for all category artifacts; v1.7 adopted as stable baseline. | Houses routing spine, release notes, and modular structure.
DL‑09 | Examples H1: Applied Continuity Scenarios | Conceptual / Applied | Concrete examples demonstrating continuity behavior across sessions, including structured memory evolution. | ai-computational-memory/examples/ | PH‑01, PH‑04 | CM‑01, CM‑04 | Enterprise reviewers, governance teams, vendors | Complete | "July 2026" | Examples referenced in white paper and FAQ; used to illustrate continuity behavior for enterprise reviewers. | Demonstrates applied continuity scenarios.
DL‑10 | FAQ H1: Category Clarification | Conceptual / Boundary Clarification | Enterprise‑grade FAQ clarifying category boundaries, regulatory alignment, and implementation considerations. | ai-computational-memory/faq/ | PH‑01, PH‑04 | CM‑01, CM‑04 | Enterprise stakeholders, regulators, governance teams | Complete | "July 2026" | FAQ used to clarify category boundaries and regulatory alignment; adopted across enterprise communications. | Provides enterprise‑grade clarification and boundary framing.
DL‑11 | White Paper v1.0 (Full 65‑page Artifact) | Category Definition / Enterprise Communication | Complete category‑defining white paper including architecture, controls, test suite, use cases, examples, FAQ, and version footer. | ai-computational-memory/white-paper/v1.0/ | PH‑01–PH‑05 | CM‑01–CM‑05 | Regulators, vendors, enterprise leadership, governance teams | Complete | "July 2026" | White paper becomes the authoritative artifact for the category; referenced across all phases and deliverables. | Complete 65‑page category‑defining document.
Note on C1: nathan myers: Spec / Code / Whitepaper / Governance Note / Regulator Brief
Note on H1: nathan myers: Vendors / Regulators / Governance / Practitioners